## Slide 1
2015
2016
Today
Nov
Dec
Jan
Feb
Mar
Apr
May
Jun
2016
Milestone 1
Nov 20 Submit revised version paper Plos One
Milestone 2
Dec 1 Submit paper to The Lancet
Milestone 4
Jan 15 deadline Journal of Translational Engineering in Health and Medicine
Nov 7
Dec 20
5 days
Task 1
Nov 20 - Revision complete, just submit the paper
16 days
Task 2
Nov 19 – Nov 25 Modify the manuscript according to co-authors comment
24 days
Task 3
Nov 25 Send paper to Bert and Martijn Spruit for final read
17 days
Task 4
Dec 1 Submit paper The Lancet
25 days
Task 5
Nov 19 - Nov 30 finalizing results
Task 6
Nov 30 – Dec 12 write paper
Task 7
Dec 12 send paper to co-authors
End of contract with TU/e
Milestone 3
Dec 18 start writing Thesis
Defense
Hopefully start a job
Milestone 4
20 Feb submit Thesis
Grey Area
Prof Watz (Pulmonary Research Institute Grosshansdorf) offered me to analyze data from 28 subjects with COPD, data from PLS and a activity monitor
  Very important to validate the last paper (analysis could be included)
Prof. Wouters (CIRO) offered me to analyze data from 10000 patients with COPD (Maastricht study) screened for OSA
  Unique opportunity
I have another work almost ready (Smart Stethoscope for which a patent was filed) that I would like to publish.
Extension of the contract for 2 months
Use >300 hours holidays
Extend contract as guest researcher
Start working
Philips contract
Numbers:
1 Journal paper accepted IEEE JBHI
1 Journal paper accepted XRDS (student magazine)
1 Journal paper submitted Plos One
1 Journal almost ready to be submitted to The Lancet
1 Journal planned (have results)
3 Patents filed
2 Conferences Papers (oral presentations)
2 Conferences Abstracts (oral presentations)
Grey Area
Committee members not available at the same time