1. Protocol written to acquire continuous data in daily life. Document revised by Martijn. 2012
2. Interrupted refining and submission because of the opportunity to join Anouk's protocols.
  Agreements:
    1. Use of Shimmer sensors
    2. Continuous recording of day of measurements
    3. Attaching-removing the sensors performed by CIRO nurses
    4. ADL data recordings performed by CIRO people, at the beginning helped by TU e (until able to do it alone).
    5. Provide with synchronized, labelled and cleaned data (accelerometer, HR, Oxycon)
    6. Intent to finish to acquire the measurements within 1 year to be used in the iCare4COPD project and in	Gabriele's thesis. (Data replaced with SenseWear data).
3. Amendment submission to include the above modifications
4. Amendment rejected (not aware of => our 1st protocol could be used because more congruent with my research (scripted activities not too interesting).
5. Submission of a new protocol containing the amendment rejected + more patients + heart failure patients.
6. Measurements started in June 2014
7. Agreements asked not included in the new submission => Writing and submission of a new amendment to
  1. Record a patient longer than only the ADL test
8. Amendment accepted end August 2014
9. Amendment not respected (often 2 ADL tests in the same day => only 1 day of “free living”)
10. End of the measurements not respected (not used for iCare4COPD, difficult to use in Gabriele's thesis.
11. Impossibility for Gabriele to go to CIRO to acquire data. Discuss about data pre-processing.